CALL FOR A PROJECT

Updated: 07.10.2008

Name: “Youth in the Election”

Action:  1.3 Youth Democracy Project

Date: February 2009 to July 2009, 6 months

Background of the Project

Voting is the main part of the democracy. A voting system allows voters to choose between options, often in an election where candidates are selected for public Office. Every country has diferent voting systems derived from its history, culture and political system.

The most of the population live in the cities.So the local goverments are always getting more attention then ever before. Local government is the tier of public authority that citizens first look to to solve their immediate social problems. It is also the level of democracy in which the citizen has the most effective opportunity to actively and directly participate in decisions made for all of society.

The question of youth electoral participation is becoming increasingly important as a focus of research, both in Turkey and internationally. Academic studies.indicated that young people vote at rates that are significantly lower than those of older generations, both in Turkey and Europe. In addition, today's youth are not showing signs of becoming more likely to vote as they age. Moreover, each successive generation appears to be less inclined to vote than its predecessors. Together, these trends suggest the recent declines in overall voter turnout will continue into the future.

The reasons for declining turnout among young people are many. Low levels of political interest and knowledge, a declining sense that voting is a civic duty, certain administrative difficulties, and limited contact with political parties and candidates are the most frequently identified factors

Introduction

Turkey is going to hold a local election on 29th March 2009. Preparation for the March 2009 local election, The Youth Governance Association is focusing on training youth to take an active role in the political life of the country and to increase ability of youth to evaluate different policical parties and theri different policies for local area in Bursa

Objectives of the Project

- Increase the awareenes of the importance of youth participation in democratic processes.

- Support young people to take an active role in the political life of the cities.

- Foster young people to get beter conciousness for their decisions in voting

- Understand the different electorol systems around Europe

- Support young people in terms of the legal and management procedures for creating and managing community, youth, charitable, and professional organizations

Activities of the Project

- Planning and Preparation

- Coordination Meeting with partners in a partner country. The place is not fixed yet. The meeting will be 2 days in February 2009. 1 youth leader from each partner ll participate to the meeting (totaly 6 pax) . During this phase and meeting, the partners will agree on the common theme of the Project. They are going to reflect on division of tasks, Seminar programme, working methods, profile of participants, practical arrangements (venue, transfers, accommodations, support material, linguistic support) and also web-site , brochures, posters, sticers, notebooks, promotional items (t-shirts, caps, pens, etc.);

Pre-training to Local Youth in Bursa, 3 days in begening of March

The training will be based on the subjects of Turkish Constutition, Turkish Electrol Law, The EU Youth Program, Youth and Participation, Active Citizenship.The youth group consists of 20 people from political parties, NGOs, Universities in Bursa.

- Implementation of the Activity

- Study Visit-Observing the Election

- This activity will take place between 24th -30th March 2009 in Bursa. Every partner organization will participate with 5 young people to the activity (4 organizations from 2 YiA programme countries + 2 organizations from Turkey; 20 + 20 young people: totally 40 participants)

1. day; workshop- get to know each other, group building activity, Project aims and program

2. day; workshop- different election system in different countries

3. day; study visit to A political party and debate and evaluation of its policy and strategy for election

4. day; study visit to A political party and debate and evaluation of its policy and strategy for election

5. day; study visit to A political party and debate and evaluation of its policy and strategy for election

6. day: observation on the local election –group based activity. making intervies with voters about their votes

7 day: evaluation on election and interviews

Post-training

The local youth participants from Bursa ll take 2 days a post-training section about the legal and management procedures for creating and managing community, youth, charitable, and professional organizations. This activity ll be hold on the begining of May 2009

- Evaluation (including reflection on a possible follow-up).

Closure Meeting

Closure meeting in a partner country. Closure meeting is about the final evaluation, and makes it possible to assess whether the objectives of the project have been achieved and the expectations of the partners and participants have been met. 1 youth leader from each partner (totally 6) ll participate to the meeting. In this meeting it is discussed about the process of meetings, outcomes of the workshops, study visit on election, trainings and follow-up of the project. The meeting ll be held in June 2009 in a partner city of the project.

###### Profile of Participants

We are going to have 3 partner countries in the project, and 2 partners from each country. Totally 5 partner organizations and including us ; 6 organizations

From each partners, 5 young people ll participate the main activity of project in Turkey.

Also 1 youth leader ll participate to both coordination and evaluation (closure) meetings

Partner Consortium

| Partners | Country | Organization |
| --- | --- | --- |
| 1 | Turkey | Association of Youth Governance |
| 2 | Turkey |  |
| 3 | Country A |  |
| 4 |  |  |
| 5 | Country B |  |
| 6 |  |  |

Materials as Outcomes of the Project

- web-site ,

- brochures 500 units,

- posters of the project 500 units,

- notebooks 500 units,

- roll-ups 2 units,

- pens 200 units,

- project final booklet in 3 different languages 700 units,

- project short movie,

- project DVDs 700 units.

###### Funding and Budget

Travel costs, Accommodation/food costs, Organisation of seminars, meetings, consultations, activities, - Publications/translations/information costs, Dissemination and exploitation of results, Other costs directly linked to the implementation of the project are covered by 75 % from the EU Grand.

Due to coo-financing,  the project  covers %70 of travel cost of each participants and %100 accommodation/food costs, Organization of seminars, meetings, consultations, activities, - publications/ translations /information costs, Dissemination and exploitation of results, Other costs directly linked to the implementation of the project

The overal budget of the project is about 55.820 euros. 42.865 Euro ll be granted by the EU.

Submitting Applications

Deadline for submitting applications: The Preliminary Agreements (Part III ) must be sent in by fax/ scanned by 20th of October and in original format within 7 days once your participation has been confirmed; successful applicantion are to be notified by 22th of October.

###### Contact

Ayshe Hacioglu

info@youthgovernance.org

Youth Governance Organization

www.youthgovernance.org

tel:  0090 224 2707056

fax: 0090 224 2707019

if any question, do not hesitate to ask.... 

note: we would be happy to hear about your addition contribution to the project as an asset

Aderess:  Kuruçeşme Mah. Gelin Sok. Seyit Usul Kültür Merkezi
Osmangazi – BURSA TURKEY

| Part III. Partner promoter(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Has also applied for this project to its National Agency : |  |  |  |  |  | Yes |  |  | No | Unknown |  |  | Not applicable |  |  |
| A. Details of the partner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Street address |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Postcode |  |  |  |  |  |  |  | City |  |  |  |  |  |  |  |
| Region |  |  |  |  |  |  |  | Country |  |  |  |  |  |  |  |
| Email |  |  |  |  |  |  |  | Website |  |  |  |  |  |  |  |
| Telephone |  |  |  |  |  |  |  | Telefax |  |  |  |  |  |  |  |
| Person in charge of the project (contact person) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Family name (Ms/Mr) |  |  |  |  |  |  |  | First name |  |  |  |  |  |  |  |
| Position/function |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Email |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Telephone |  |  |  |  |  |  |  | Telefax |  |  |  |  |  |  |  |
| B. Profile and role of the partner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type and status | Non profit/non governmental organisation |  |  |  | Public body Informal group of young people |  |  |  |  |  |  |  |  |  |  |
|  | Body active at European level in the field of youth (ENGO) |  |  |  | Other – please specify: |  |  |  |  |  |  |  |  |  |  |
| Activity level | Local |  | Regional |  |  |  | National |  |  |  |  | European/International |  |  |  |
|  | Member organisation of the applicant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Role | Sending Organisation |  |  | Host Organisation |  |  |  |  |  |  |  |  |  |  |  |
| Please give a short description of your organisation/group (regular activities, member of, etc.): |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| C. Preliminary agreement of the partner |  |  |  |
| --- | --- | --- | --- |
| I, the undersigned, on behalf of (repeat the name of the partner) |  |  |  |
| confirm our participation in each stage of the project (repeat the title of the project as stated in Part I): “Youth in the Election” |  |  |  |
| In case of one-sided funding, I declare having reached an agreement with all the promoters involved in the project with regard to the share of EU grant my organisation/group is entitled to receive in order to implement the project. Furthermore, I confirm my undertaking to ensure visibility of the European Union support for the project and to ensure dissemination and exploitation of its results. |  |  |  |
| Name in capital letters: |  |  |  |
| Place: |  | Signature: |  |
| Date: |  |  |  |